## Sheet1
Activity ID | Activity Name | Start date | Finish date | Resources (FTE) | Names | Status | Comments
Alignment 1 | 2D model development and testing millepede build. | 2015-11-15 | 2015-12-16 | 0.6 | Gilfoyle, Davies(?) | started
Alignment 2 | 3D model development and millepede test. | 2015-12-17 | 2016-01-13 | 0.6 | Gilfoyle, Davies(?) | Planned
Alignment 3 | SVT algorithm development and integration with reconstruction | 2016-01-13 | 2016-03-31 | 0.6 | Gilfoyle, Davies(?) | Planned
Alignment 4 | Algorithm MC tests | 2016-04-01 | 2016-04-30 | 0.6 | Gilfoyle, Davies(?) | Planned
Alignment 5 | Cosmic ray analysis | 2016-05-01 | 2016-05-31 | 0.6 | Gilfoyle, Davies(?) | Planned
FTOF 1 | Validation of existing algorithms | 2015-12-02 | 2016-01-06 | 0.4 | Golovach | started
FTOF 2 | Combine FTOF 1a and 1b timing to improve resolution. | 2016-01-07 | 2016-02-15 | 0.4 | Golovach | planned
FTOF 3 | Match hits/clusters in the two panels 1a and 1b | 2016-02-16 | 2016-03-31 | 0.4 | Golovach | planned
CTOF1 | Validation of existing algorithms | 2016-04-01 | 2016-04-30 | 0.4 | Golovach | planned